Digital Audio Denmark DAD Documentation & Content Platform Project Plan · Timeline · Budget · Risk Register June 2026 · Version 1.0 · Confidential

# Executive Summary

This document outlines the plan to build a comprehensive, standards-compliant documentation and content platform for Digital Audio Denmark’s product portfolio. Beginning with the DADman control software, the initiative has three interconnected objectives:

- Build a professional-grade DADman User Manual to IEC/IEEE 82079-1:2019 and IEC 62368-1 standards, benchmarked against leading industry manufacturers (SSL, LAWO, Yamaha, DigiCo).

- Establish a living documentation infrastructure on GitHub + Docusaurus — version-matched to each firmware release, multi-product capable, and continuously maintained with AI assistance through Claude/Cowork.

- Create an automated content pipeline that generates tutorials, release notes, knowledge base articles, and marketing copy directly from the structured manual as a single source of truth.

The project runs across five phases over approximately six months. The core technology stack is open-source and free; ongoing infrastructure costs are minimal. The primary investment is team time, with Claude/Cowork providing AI-assisted drafting throughout every phase.

# Project Snapshot

| Project Lead | Jon Schumann, Digital Audio Denmark |
| --- | --- |
| Team | Jon + small cross-functional team (engineering, product, content) |
| Product Portfolio | Core 256 · Core256 Racking Hardware (just announced) · AX Center · AX 64 · MOM · DAD Junior · MOM2 (pre-announcement — confidential) · Future launches (readiness is critical) |
| Source Material | Existing partial manual (to be audited and restructured in Phase 1) |
| Documentation Standard | IEC/IEEE 82079-1:2019 · IEEE 1063 · IEC 62368-1 (safety) |
| Technology Stack | GitHub + Docusaurus + Claude/Cowork + GitHub Actions + GitHub Pages |
| Target Launch | DADman Manual v1.0 — as soon as possible; no hard deadline |
| Estimated Cost | €1,000–5,000 one-time setup · €20–50/month ongoing |

# Phase Plan & Timeline

The project is structured in five sequential phases. Phases 1 and 2 are the critical path to v1.0 publication. Phases 3–5 build the infrastructure and automation that make the documentation a continuously valuable, living asset.

Phase 1 — Discovery & Foundation Weeks 1–3

## Objectives

- Audit the existing partial DADman manual and all scattered documentation (spec sheets, release notes, KB articles, engineering notes)

- Map discovered content against the canonical 10-chapter structure; identify and size the gaps

- Set up the GitHub repository and Docusaurus project (two product directories: /dadman, /ax32)

- Define the team review and approval workflow; assign chapter reviewers

- Confirm which DADman firmware version v1.0 of the manual will cover

## Key Deliverables

| Deliverable | Description | Owner |
| --- | --- | --- |
| Content inventory & gap map | Full audit of all existing docs against the 10-chapter template; gaps sized by effort | Jon |
| GitHub repository | Docusaurus project with /dadman and /ax32 dirs; initial GitHub Actions CI/CD workflow | Developer |
| Approved chapter outline | Section-level outline for the full DADman manual, signed off by the team before drafting begins | Jon + Eng |

Phase 2 — DADman Manual: Full Draft Weeks 3–10

## Approach

Each chapter is drafted by Claude (using the pro-audio-manual-expert skill), reviewed by a DAD engineer for technical accuracy, revised, and signed off. The cycle is per-chapter — not a single end-to-end pass. This keeps review sessions manageable and allows parallel progress.

## Chapter Plan

| # | Chapter | Key Content | Est. Effort | Reviewer |
| --- | --- | --- | --- | --- |
| FM | Front Matter & Safety Notices | IEC 62368-1 notices, compliance declarations, signal word definitions | 2 days | Eng + Legal |
| 1 | Introduction & Product Overview | Feature list, signal flow block diagram, documentation map | 2 days | Product |
| 2 | System Requirements & Package Contents | OS versions, hardware reqs, package checklist | 1 day | Engineering |
| 3 | Installation | Hardware rack install, software install, license activation, first power-on | 3 days | Engineering |
| 4 | Hardware Description | Annotated front/rear panel diagrams, LED state table | 3 days | Engineering |
| 5 | Signal Flow & Architecture | Block diagrams, clocking hierarchy, format matrix, latency figures | 3 days | Engineering |
| 6 | Getting Started | 10-step quick setup walkthrough, cross-refs to full chapters | 2 days | Engineering |
| 7 | Operation | 7 workflow sections: session mgmt, I/O, clocking, gain, network, monitoring, DADman-specific | 8 days | Engineering |
| 8 | Advanced Features | Advanced DADman capabilities, integrations, macros | 4 days | Engineering |
| 9 | Troubleshooting | Symptom ¦ Cause ¦ Remedy tables; all known failure modes | 3 days | Eng + Support |
| 10 | Maintenance | Firmware update procedure, cleaning, storage, EOL disposal | 2 days | Engineering |
| App | Appendices A–H | Specs, pinouts, formats, shortcuts, changelog, compliance, glossary, index | 5 days | Eng + Legal |

## Deliverable

DADman User Manual — complete draft, all chapters written, technically reviewed, and ready for Phase 3 QA. Stored in the GitHub repository as Markdown source files.

Phase 3 — Review, QA & Publication Weeks 10–14

## Objectives

- Complete the final round of internal technical review across all chapters

- Obtain regulatory sign-off on CE, FCC, and RoHS compliance declarations

- Configure GitHub Actions for automatic deployment: merge to main → docs rebuild and publish

- Set up PDF export (one download per product, per version) and Algolia full-text search

- Publish DADman Manual v1.0 to the live documentation site

## Deliverables

- DADman User Manual v1.0 — live web version at docs.digitalaudio.dk + downloadable PDF

- Automated deployment pipeline operational — push a tag, docs update automatically

- Algolia DocSearch configured and indexed across all product documentation

Phase 4 — Content Automation Pipeline Weeks 14–18

## Objective

Build the pipeline that allows the manual to automatically spawn derivative content when features are added or firmware is released. The manual becomes the single source of truth for the entire content ecosystem.

| Content Type | Source (Manual Section) | Trigger |
| --- | --- | --- |
| Tutorial script | Chapter 7 — Operation sections | New workflow section merged to main |
| Feature release notes | Appendix E — Changelog | Firmware version tag pushed |
| Knowledge base article | Chapter 9 — Troubleshooting table | New symptom row added |
| Marketing copy | Chapter 1 — Features overview | Major feature addition |
| Quick start PDF | Chapter 6 — Getting Started | New product or major version |
| Support FAQ | Chapters 7 + 9 | Weekly scheduled generation |

## Deliverable

Operational content pipeline: GitHub Actions triggers + companion Claude skills for each content type. Tested against the next real DADman firmware release.

Phase 5 — Full Product Portfolio Rollout Weeks 18–36+

## Overview

DAD has a seven-product portfolio requiring documentation, with one pre-announcement product (MOM2) and a critical requirement that the platform is ready to onboard future launches rapidly. Phase 5 builds out the full suite in priority order while simultaneously establishing the infrastructure that makes each subsequent product faster than the last.

## Product Documentation Roadmap

| Product | Priority | Est. Effort | Notes |
| --- | --- | --- | --- |
| Core 256 | P1 — Urgent | 6–8 weeks | Flagship product; highest visibility; hardware + DADman integration docs |
| Core256 Racking Hardware | P1 — Urgent | 2–3 weeks | Just announced — immediate documentation priority; hardware installation + integration guide |
| AX Center | P2 | 4–5 weeks | Hardware manual; signal flow and integration with Core 256 ecosystem |
| AX 64 | P2 | 4–5 weeks | Hardware manual; shares structure with AX Center; content reuse possible |
| MOM | P3 | 4–5 weeks | Hardware + software manual; unique workflow considerations |
| DAD Junior | P3 | 3–4 weeks | Entry-level product; simpler manual; strong "getting started" emphasis |
| MOM2 | P4 — CONFID. | TBD | CONFIDENTIAL — pre-announcement. Platform structure and shared content library ready before launch; manual drafted under embargo and published on announcement day |

## Future Launch Readiness — Critical Requirement

Readiness for future product launches is a first-class design requirement for the entire documentation platform, not an afterthought. The following capabilities must be operational before Phase 5 completes:

- New-product onboarding template: a pre-configured Docusaurus directory, GitHub Actions workflow, and chapter outline that can be forked for any new DAD product in under a day

- Shared content library: safety notices, compliance declarations, company information, and brand elements authored once and referenced by all product manuals — eliminating duplicate maintenance

- Embargo workflow: a documented process for drafting, reviewing, and publishing a product manual under NDA, with automated publication triggered on announcement day

- Pre-populated structure for MOM2: directory structure, front matter, and chapter outline created before the product is announced, so documentation is not on the critical path at launch

- Content pipeline integration: the automated tutorial, release note, and KB generation pipeline operational for all products from day one of their manual being published

## Deliverable

All announced product manuals v1.0 published. MOM2 documentation ready for day-one announcement publication. Shared content library operational. New-product onboarding process documented and tested. The platform scales to any future DAD product without infrastructure changes.

# Timeline Overview

| Phase | Month 1 | Month 2 | Month 3 | Month 4 | Month 5–6 |
| --- | --- | --- | --- | --- | --- |
| Phase 1 — Discovery & Foundation | ███ |  |  |  |  |
| Phase 2 — DADman Manual Draft | ███ | ███ |  |  |  |
| Phase 3 — Review, QA & Publication |  | ███ | ███ |  |  |
| Phase 4 — Content Automation |  |  |  | ███ |  |
| Phase 5 — Full Portfolio Rollout (7 products) |  |  |  |  | ███ |

# Team & Resources

## Internal Team

| Role | Time Commitment | Responsibilities |
| --- | --- | --- |
| Project Lead (Jon) | 4–6 hrs/week | Direction, content review, stakeholder decisions, Claude sessions, final approval on all content |
| Senior Engineer ×1 | 2–3 hrs per chapter | Technical accuracy review; spec sheet and signal flow validation; regulatory data |
| Product / Support | 1–2 hrs/week | Troubleshooting table review; user workflow validation; support contact info |
| Developer (setup) | 1–2 days (one-time) | GitHub repo, Docusaurus config, GitHub Actions CI/CD pipeline, Algolia integration |
| Legal / Compliance | 2–4 hrs (one-time) | Review and sign off on CE, FCC, RoHS, and WEEE compliance declarations in Appendix F |

## Technology Stack

| Tool | Role in Project | Status |
| --- | --- | --- |
| Claude / Cowork | Primary drafting, QA, content generation, automation orchestration | Active — existing subscription |
| pro-audio-manual-expert skill | Expert persona, IEC/IEEE standards, industry conventions, quality checklist | Built — installed this session |
| GitHub | Version control, PR-based review workflow, CI/CD triggers | Setup required in Phase 1 |
| Docusaurus | Documentation site framework; native versioning per product | Setup required (open-source, free) |
| GitHub Actions | Auto-build and publish on firmware release tags | Configured in Phase 1 |
| GitHub Pages | Public hosting for the documentation site | Free with GitHub |
| Algolia DocSearch | Full-text search across all products and versions | Free for public documentation |

# Budget & Cost Estimate

The technology stack is open-source and largely free. Costs are concentrated in two areas: a one-time setup investment (developer time, optional design and compliance work) and a small ongoing subscription for GitHub.

## One-Time Setup Costs

| Item | Type | Estimate | Notes |
| --- | --- | --- | --- |
| Docusaurus + GitHub setup | Internal time | 1–2 days | Can be Jon or a developer; requires Node.js and basic git familiarity |
| GitHub Actions CI/CD config | Internal time | 0.5 day | Automated build-and-deploy pipeline |
| Domain (docs.digitalaudio.dk) | External | €10–15/year | If not already registered; amortised to <€2/month |
| Technical block diagrams | Design (optional) | €500–2,000 | If professional vector illustrations needed; Claude can produce draft versions |
| Regulatory compliance review | Legal / compliance | €500–1,500 | External review of CE/FCC/RoHS declarations; required before publishing |
| TOTAL ONE-TIME |  | €1,000–5,000 | Range depends on design and compliance scope |

## Ongoing Monthly Costs

| Item | Monthly Cost | Notes |
| --- | --- | --- |
| Claude / Cowork subscription | Existing | No additional cost — already in active use for this project |
| GitHub Team (private repo, 5 users) | €20/month | €4/user/month; €0 if the documentation repository is made public |
| GitHub Pages hosting | Free | Included with all GitHub plans |
| Algolia DocSearch | Free | Free for public-facing open documentation |
| Domain renewal | ~€1/month | Amortised annual registration cost |
| TOTAL ONGOING | €20–50/month | Primarily GitHub Team; all other infrastructure is free |

# Risk Register

Each risk is rated for likelihood and impact. Mitigations are built into the phase plan where possible.

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Engineering review is the bottleneck — limited time means chapters stall awaiting technical sign-off | High | High | Schedule review slots in Phase 1 before drafting begins; batch multiple chapters per session; Claude produces a QA pass first so engineering review is corrections, not first read |
| Source material gaps — the existing partial manual has undocumented features or outdated procedures | High | Medium | Phase 1 gap analysis sizes this early; schedule dedicated engineering sessions to fill gaps; document what is known and explicitly flag unknowns rather than guessing |
| Firmware changes during drafting — DADman features shift before the relevant chapter is complete | Medium | Medium | Pin Manual v1.0 to a specific firmware version at the start of Phase 2; document delta sections for subsequent releases rather than rewriting mid-draft |
| Screenshot drift — UI screenshots become outdated with each software update | Medium | Low | Policy: screenshots refreshed on major releases only; source screenshots stored in the repo with version tags; Claude flags version mismatches on review |
| Regulatory sign-off delay — CE/FCC compliance declarations need a named authorised signatory | Low | High | Identify the authorised signatory in Phase 1; initiate compliance review at the start of Phase 3, not the end; prepare draft declarations early |
| Team adoption of the GitHub workflow — engineers accustomed to Word/email may resist | Medium | Medium | GitHub web UI allows editing without a terminal; Jon acts as the integration point for non-git contributors; process kept as simple as possible in Phase 1 |
| Content quality inconsistency — multiple contributors produce sections in differing styles | Low | Medium | All content passes through the pro-audio-manual-expert skill before finalisation; Claude enforces consistent formatting, tone, and information typing |
| Multi-language requirements — international markets may require translated documentation | Low | High | Docusaurus has native i18n support; structure content for translation-readiness from the start: no idioms, consistent terminology, short imperative sentences |

# Success Metrics

| Metric | Target / Definition of Done |
| --- | --- |
| DADman Manual v1.0 published | Live on docs site with PDF download; all chapters technically reviewed and signed off |
| IEC/IEEE 82079-1 compliance | Every chapter passes the quality checklist in the pro-audio-manual-expert skill; safety notices correctly tiered |
| Automated deployment operational | Merge to main → docs rebuild and publish within 10 minutes, without manual steps |
| First automated content piece | Tutorial script or release note generated automatically from the next firmware release tag |
| Core 256 + Core256 Racking Hardware manuals published | Priority P1 — first products after DADman; both treated as urgent |
| All P2 & P3 product manuals published | AX Center, AX 64, MOM, DAD Junior — all live with PDF download by end of Phase 5 |
| MOM2 documentation ready at announcement | Manual drafted under embargo; published automatically on announcement day — zero lag |
| Future launch readiness operational | New product onboardable in under 1 day; shared content library live; embargo workflow tested |
| Documentation discoverability | Site indexed by search engines; linked from digitalaudio.dk support and product pages |
| Support ticket reduction | Measurable reduction in queries covering documented topics; target −20% within 3 months of v1.0 launch |

# Immediate Next Steps (Week 1)

To initiate Phase 1, the following five actions should be completed before the next working session:

- Gather all existing DADman documentation — partial manual, release notes, spec sheets, knowledge base articles, engineering notes — into a shared location accessible to Claude.

- Identify the GitHub account or organisation to use for the documentation repository. Decide: public or private repo (public = zero hosting cost and free Algolia search).

- Confirm the DADman firmware version that Manual v1.0 will document. This pins the scope and prevents mid-draft scope changes.

- Identify the developer or engineer who will handle the Docusaurus and GitHub Actions setup (Phase 1 dependency; 1–2 day task).

- Schedule the first chapter review session with the engineering contact who will be the primary technical reviewer.

Note on scope: the AX32 is end-of-life and is explicitly excluded from this project. All documentation effort targets the active and upcoming product portfolio listed above.

Claude and Cowork are ready to begin immediately. The pro-audio-manual-expert skill is installed and active. The next session can start directly with a content audit of the existing partial DADman manual.

DAD Documentation & Content Platform · Project Plan v1.0 · June 2026 · Prepared with Claude / Cowork